## Slide 1
BRIEFING
DECISION DECK
Q2 grew, but supply
reliability missed
Northwind Mobility Q2 2028 QBR. Growth remained strong and unit economics
improved, but fleet availability missed plan because battery refurbishment capacity did
not keep pace with the fleet.
Executive decision required: approve the Q3 recovery spend and defer Eastmere so
reliable supply comes before faster expansion.
DECISION DECK
Notes: This is a read-led QBR for the Northwind Mobility executive team. The headline is balanced: the commercial engine is working, but the operating constraint has moved to battery refurbishment and availability.

## Slide 2
02 VERDICT
DECISION DECK
Verdict: recovery should prioritize supply, not expansion
€12.84m
Q2 revenue, 2.7% below plan
Miss: €0.36m
41.8%
Gross margin, 1.3 pp above plan
+2.2 pp vs Q1
91.6%
Fleet availability, 3.4 pp below plan
Operating constraint
€0.74m
Operating cash flow, €0.22m above plan
Cash improving
Executive take: Q2 was not a demand failure. Subscriber growth and margin improved, but unavailable bikes reduced subscription months, lifted churn and held back
NPS. The Q3 plan should spend €0.50m to restore capacity and avoid €0.86m Q3 Eastmere cash use.
Source: user brief. Values are fictional.
02 / 12
Notes: The verdict is that Q2 performance was commercially healthy but operationally constrained. The recovery plan is therefore about reliable supply rather than new-city acceleration.

## Slide 3
03 SCORECARD
DECISION DECK
The scorecard shows growth and margin, with availability red
METRIC
Q2 ACTUAL
Q2 PLAN
Q1 ACTUAL
Q2 VS PLAN
STATUS
Revenue
€12.84m
€13.20m
€11.46m
−2.7%
WATCH
Active subscribers
38,420
39,000
35,880
−1.5%
WATCH
Net adds
2,540
3,120
2,310
−580
WATCH
Gross margin
41.8%
40.5%
39.6%
+1.3 pp
AHEAD
Monthly churn
2.9%
2.6%
3.1%
+0.3 pp
WATCH
Fleet availability
91.6%
95.0%
93.8%
−3.4 pp
OFF PLAN
NPS
48
52
46
−4
WATCH
Operating cash flow
€0.74m
€0.52m
€0.18m
+€0.22m
AHEAD
Source: user brief. Status is working judgment based on Q2 versus plan.
03 / 12
Notes: The scorecard makes the operating constraint visible. Margin and cash are ahead of plan, but availability is the clear red item and it is pulling on revenue, churn and customer experience.

## Slide 4
Chart: 
| Unavailable bikes | Accessories | Corporate activation | Avg. price
Revenue variance, €m | -0.24 | -0.17 | -0.08 | 0.13
€0.24m fewer subscription months from unavailable bikes.
€0.17m lower accessory sales.
€0.08m slower corporate-plan activation.
€0.13m higher average subscription price offset part of the gap.
04 REVENUE BRIDGE
DECISION DECK
Unavailable bikes explain most of the revenue miss
The €0.36m gap versus plan was driven by fewer subscription months
from bike unavailability. Price helped, but did not offset availability,
accessory and corporate activation pressure.
Source: user brief. Bridge values sum to −€0.36m after rounding.
REVENUE BRIDGE, €M VS PLAN
04 / 12
Notes: This bridge separates demand, monetization and supply. The dominant negative is fewer subscription months because bikes were not available, which confirms that supply reliability is the right recovery theme.

## Slide 5
Chart: 
| Price and mix | Field maintenance | Procurement | Expedited battery logistics
Gross margin change, pp | 1.1 | 0.8 | 0.6 | -0.3
05 MARGIN BRIDGE
DECISION DECK
Margin improved because price, maintenance
and procurement outweighed logistics
GROSS MARGIN BRIDGE, PP VS Q1
39.6%
Q1 gross margin
baseline
41.8%
Q2 actual gross margin
+2.2 pp
Margin quality improved in Q2, but one offset is
directly tied to the availability problem: expedited
battery logistics reduced gross margin by 0.3 pp.
Source: user brief.
05 / 12
Notes: The margin story is positive and should not be lost. However, even the margin bridge shows the cost of the availability constraint through expedited battery logistics.

## Slide 6
06 CITY COMPARISON
DECISION DECK
Westhaven and Bellweather
carry the availability pressure
CITY
Q2 REVENUE
YOY GROWTH
SUBSCRIBERS
AVAILABILITY
MONTHLY CHURN
READOUT
Northport
€4.18m
18%
12,480
94.2%
2.5%
STABLE
Linden
€3.36m
24%
10,140
92.1%
2.8%
WATCH
Westhaven
€2.91m
31%
8,960
89.4%
3.4%
CONSTRAINED
Bellweather
€2.39m
27%
6,840
88.7%
3.2%
CONSTRAINED
Management implication: availability-aware acquisition caps should apply first in Westhaven and Bellweather, where growth is high but
availability is below 90% and churn is above the company average.
Source: user brief. Readout is working judgment based on availability and churn.
06 / 12
Notes: The city view makes the recovery plan more targeted. Northport is near plan, while Westhaven and Bellweather should not keep adding demand until swap reliability improves.

## Slide 7
Chart: 
| Battery refurbishment | Mechanical repair | Awaiting parts | Damage assessment | Other
Unavailable bikes | 612 | 334 | 196 | 153 | 116
07 AVAILABILITY DIAGNOSIS
DECISION DECK
Battery refurbishment is the
largest availability bottleneck
UNAVAILABLE BIKES AT QUARTER END
1,411
Bikes unavailable at
quarter end
16,800
Average fleet in Q2
14.6d
Median battery
turnaround, up from
8.2d
Slower
2,640
Support contacts about
unavailable swap bikes
Q1 was 1,820
Source: user brief.
07 / 12
Notes: Battery refurbishment is the leading cause of unavailable bikes, well ahead of mechanical repair and parts. The customer signal confirms the operational metric: support contacts on unavailable swap bikes rose sharply.

## Slide 8
Chart: 
| Demand | Current capacity | Recovery capacity
Units per week | 238 | 202 | 295
08 CAPACITY PLAN
DECISION DECK
The Q3 capacity plan closes the 36-unit weekly gap
238
Weekly battery refurbishment demand in Q2
202
Current weekly capacity: 170 internal plus 32 external
36-unit gap
295
Recovery weekly capacity: 225 internal plus 70 external
57-unit cushion
BATTERY REFURBISHMENT UNITS PER WEEK
Required landing: add the second internal battery shift by 22 July and contract
70 external units per week from 12 August.
Source: user brief. Recovery capacity equals 225 internal plus 70 external.
08 / 12
Notes: The capacity math is simple and decisive. Today, total capacity is 36 units per week short of demand, while the proposed Q3 actions create a 57-unit cushion if executed on time.

## Slide 9
Q3 SCENARIO | CONDITION | REVENUE | SUBSCRIBERS | GROSS MARGIN | AVAILABILITY | MONTHLY CHURN
Downside | External refurbishment starts four weeks late | €13.21m | 39,980 | 41.5% | 91.9% | 3.2%
Base forecast | Current recovery pacing | €13.62m | 40,650 | 42.4% | 93.8% | 2.8%
Recovery case | Capacity actions land by 15 August | €13.88m | 41,120 | 42.2% | 95.1% | 2.6%
09 Q3 FORECAST
DECISION DECK
Recovery case adds €0.26m revenue and restores availability
+€0.26m
Recovery revenue over base
+470
Recovery subscribers over base
+1.3 pp
Recovery availability over base
−0.2 pp
Recovery margin vs base due to spend
Source: user brief. Scenario deltas are derived from supplied scenario values.
09 / 12
Notes: The forecast makes the tradeoff explicit. The recovery case costs a small amount of margin versus base, but it restores availability and churn while lifting revenue and subscribers.

## Slide 10
10 RISK BOARD
DECISION DECK
Execution risks are known, and
each needs an accountable owner
RISK
PROBABILITY /
IMPACT
BUSINESS EFFECT
OWNER
MITIGATION
STATUS
External supplier
qualification slips
Medium / high
Downside scenario if external
refurbishment starts four weeks
late
Not
assigned
Lock qualification path and
escalation for 70 units per week
TOP RISK
Second-shift hiring fills
only 9 of 14 roles
Medium /
medium
Internal capacity uplift misses 225
units per week
Not
assigned
Daily hiring funnel review until
roles are filled
WATCH
Acquisition caps reduce
Q3 net adds by up to 420
High / low
Subscriber growth slows while
reliability recovers
Not
assigned
Cap Westhaven and Bellweather
first, monitor churn weekly
TRADEOFF
Aged battery returns
exceed forecast by 8%
Medium /
medium
Refurbishment demand rises
above planned capacity
Not
assigned
Review returns weekly and pull
external volume forward if
needed
WATCH
Source: user brief. Risk owners were not supplied and must be assigned in the QBR.
10 / 12
Notes: The main risk is not whether the plan is conceptually right, but whether the supply-side actions land on time. The brief does not assign owners to these risks, so each owner remains not assigned and must be confirmed in the QBR.

## Slide 11
WORKSTREAM | ACTION | DUE | Q3 COST / CASH EFFECT | OWNER | MEASURE OF DONE
Operations | Add a second internal battery shift, raising weekly capacity from 170 to 225 | 22 July | €0.19m cost | Samira Holt | 225 units per week internal capacity
Procurement | Contract 70 external refurbishment units a week | 12 August | €0.31m cost | Emil Voss | Qualified supplier live at 70 units per week
Product | Introduce availability-aware acquisition caps in Westhaven and Bellweather | 15 July | Not specified | Jo Neri | Caps live and reviewed weekly
Customer | Offer proactive swap reservations to 2,400 high-usage subscribers | 29 July | Not specified | Lena Arvid | 2,400 subscribers offered reservations
Expansion | Defer Eastmere launch from October 2028 to February 2029 | Q3 decision | €0.86m Q3 cash use avoided | Executive team | Launch plan reset and spend held
11 Q3 ACTION PLAN
DECISION DECK
Five owned actions shift Q3 from growth chasing to reliable supply
Source: user brief. Unspecified costs are left as not specified rather than estimated.
11 / 12
Notes: This slide converts the recovery plan into commitments. Two actions require spend, two shape demand while reliability recovers and one prevents expansion cash from competing with the supply recovery.

## Slide 12
12 DECISION
DECISION DECK
Decision: fund recovery and defer Eastmere
Approve €0.50m Q3 recovery spend to add
internal and external battery refurbishment
capacity, restore availability and protect churn.
SPEND
€0.19m + €0.31m
Second internal shift plus
70 external refurbishment
units per week.
TARGET
95.1% availability
Recovery case if capacity
actions land by 15
August.
Defer Eastmere from October 2028 to February
2029, avoiding €0.86m Q3 cash use while the fleet
recovery is executed.
Decision due: this QBR. The August 15 recovery-case gate
depends on immediate approval and owner alignment.
Source: user brief. Values are fictional.
12 / 12
Notes: The requested decision is to approve the recovery spend and defer Eastmere. This closes the deck by moving from diagnosis to action: make reliable supply the Q3 priority and delay expansion cash until the constraint is fixed.