## Slide 1
01 OPERATING REVIEW
ASTER RELAY
Fictional operating review · Week 6
Aster Relay
operating review
Eight service hubs · dispatch-platform rollout
17 September 2029Decision meeting

## Slide 2
Chart: 
| W1 | W2 | W3 | W4 | W5 | W6
On time | 86 | 88 | 90 | 92 | 93 | 93.2
Target | 95 | 95 | 95 | 95 | 95 | 95
Six hubs are stable; Central blocks the final two
Proceed with six hubs and clear the routing gate before expanding
93.2%
On time · target 95%
88%
First-time fix · target 90%
146
Open jobs · target ≤120
€84k
Weekly benefit · target €100k
RECOVERY IS REAL, BUT BELOW GATE
DOMINANT EXCEPTION
Central routing creates 64 open jobs
It holds back €16k of the €100k weekly target.
Gate · 24 Sep

## Slide 3
HUB | STATUS | OPEN JOBS | NEXT EVIDENCE
North |  | 18 | 95.4% on time
East |  | 31 | Training 20 Sep
South + five hubs |  | 33 | Benefits sustained
Central |  | 64 | Routing gate 24 Sep
One hub changes the rollout answer
Six of eight hubs are stable; Central owns 64 of 146 open jobs.
EXCEPTION THAT MATTERS
Central cannot scale on manual routing
It contributes the full €16k weekly benefit gap
and delays the final two hubs.
Owner · Mara I.
Decision today
Assign two integration engineers through the 24 September evidence gate.
STABLE
WATCH
STABLE
BLOCKED

## Slide 4
Every hub depends on one routing service
Central still uses manual queues when the dispatch orchestrator misses a location event.
01 · DEMAND
Field intake
Jobs and location
02 · SHARED DEPENDENCY
Dispatch orchestrator
Priority and route
03 · DELIVERY
Technician mobile
Sequence and proof
04 · EVIDENCE
Operations ledger
Time, outcome, benefit
critical event
ordered route
closed job
IF IT FAILS
Central falls back to manual queues
Travel rises and 64 jobs remain open.
CONTROL
Reconcile every 15 minutes
Alert the duty owner after two missed
events.

## Slide 5
Chart: 
| W1 | W2 | W3 | W4 | W5 | W6
On time | 86 | 88 | 90 | 92 | 93 | 93.2
Gate | 95 | 95 | 95 | 95 | 95 | 95
On-time service recovered by 7.2 points
The six stable hubs improved every week; Central keeps the network 1.8 points below the rollout gate.
On-time service
95% rollout gate
Fictional weekly operating ledger · 410 completed jobs per week at Week 6.

## Slide 6
The final rollout holds if routing clears on 24 September
Integration controls the date; training controls whether the expansion creates value.
SEP W3
SEP W4
OCT W1
OCT W2
Routing
MARA
Repair events
Two engineers
Monitor
Two releases
Evidence
ELENA
Gate pack
24 Sep review
Decision
Go / hold
Adoption
JONAS
Champions
32 trained
Readiness
Gate 2
Final hubs
Two sites
Gate 1 · Routing
Clear by 24 Sep or hold two hubs.
Gate 2 · Readiness
32 champions pass the live scenario.
NEXT ACTION
Book the evidence review
Elena · 24 Sep · decision in room
Rollout rule
Protect the routing gate; reduce scope rather than accepting manual queues.

## Slide 7
Jobs stall at routing, not in the field
The service is fast after assignment; Central's manual queue creates the 27-minute loss.
1
Request
Customer submits job and location.
MEASURE
96% complete first time
2
Route
Manual queue at Central when events fail.
BOTTLENECK
42 min · target 15
3
Resolve
Technician follows ordered jobs.
MEASURE
88% first-time fix
4
Close
Outcome writes to the ledger.
MEASURE
93.2% on time
Control at routing
Reconcile events every 15 minutes; alert Mara after two misses. Expected effect: recover 27 minutes and €16k per week.

## Slide 8
Six stable hubs create €84k each week
410
Completed jobs / week
37 min
Saved per job
€84k
Weekly benefit
6 / 8
Stable hubs
€34k
€24k
€16k
€10k
Labour
€34k
Travel
€24k
Repeat visits
€16k
Administration
€10k
Value gate
Central's routing repair closes the remaining €16k gap to the €100k weekly target.

## Slide 9
Three decisions protect the rollout
Keep the six stable hubs moving while the shared routing dependency is repaired.
01 · APPROVE
Two integration engineers
Owner · Elena V.
Date · Today
Impact · Recover €16k / week
02 · HOLD
Final two hubs at the gate
Owner · Mara I.
Date · 24 Sep
Impact · No manual routing debt
03 · LOCK
Champion coverage
Owner · Jonas K.
Date · 20 Sep
Impact · 32 trained operators
Decision rule
Expand only when routing clears and every final-hub shift has a trained champion.

## Slide 10
Recommendation
Proceed with six.
Earn the final two.
Clear Central's routing gate before expansion. Do
not trade a visible date for invisible operating debt.
Next action · 24 September
Review routing evidence, champion readiness and the €16k weekly value gap in one go / hold
decision.